## Plan
Project Plan: Student Course Recommendation System
Task | Start Date | End Date | Status | Name
Initial Project Paper & Proposal | 2016-02-23 | 2016-02-23 | Complete | All
Confirm Data Structure with university | 2016-03-01 | 2016-03-08 | In Progress | Follow up with Professor | Class Milestone
Database structure design | 2016-03-01 | 2016-03-08 | Not Started | All | Complete
Mock Data Creation (Excel) | 2016-03-08 | 2016-03-15 | Not Started | Ajai | In Progress
Mongo DB data loads | 2016-03-08 | 2016-03-15 | Not Started
Team Connect | 2016-03-18 | 2016-03-18 | Not Started | All
Python Logic development | 2016-03-15 | 2016-03-29 | Not Started | Keyur/Karolina
Milestone: Team project update #2 prep | 2016-03-15 | 2016-03-29 | Not Started
Team Connect | 2016-04-01 | 2016-04-01 | Not Started | All
Website development | 2016-03-22 | 2016-04-05 | Not Started | Keyur
Tableau development | 2016-04-06 | 2016-04-19 | Not Started
Team Connect | 2016-04-08 | 2016-04-08 | Not Started | All
Milestone: Team project Update #2 | 2016-03-23 | 2016-03-30 | Not Started
Test | 2016-03-23 | 2016-04-06 | Not Started
Milestone: Final Project Proposal Design Update Prep | 2016-03-23 | 2016-04-06 | Not Started
Team Connect | 2016-04-15 | 2016-04-15 | Not Started | All
Team Connect | 2016-04-22 | 2016-04-22 | Not Started | All
Team Connect | 2016-04-29 | 2016-04-29 | Not Started | All
Milestone: Team Project: Final Presentation | 2016-04-13 | 2016-05-04 | Not Started

## Main Table
Student Name | Course Name | Professor | Year Taken | Semester Taken | Course Rating | Professor Rating
Mabel Lohr | Advanced Algorithm Design and Implementation | Vallie Ruse | 2003 | Fall | 3.5 | 0
Pei Nagel | Introduction to Financial Risk Management | Dawne Aube | 2009 | Spring | 1.5 | 0
Cristine Deming | Introduction to Financial Risk Management | Kerstin Sickler | 2014 | Fall | 2.5 | 4
Effie Endicott | Data Warehousing and Business Intelligence | Henry Metzger | 2001 | Spring | 3.5 | 4
Shonda Mccarter | Risk Management Methods & Applications | Buford Bjerke | 2002 | Fall | 3.5 | 5
Janita Banaszak | Strategic Data Management | Randolph Lundell | 2001 | Fall | 3.5 | 1
Johnsie Devaughn | Introduction to Cloud Computing | Hedy Linz | 2009 | Summer | 3.5 | 2
Quentin Brumsey | Concurrent Programming | Salley Lex | 2001 | Spring | 3.5 | 0
Farah Villafuerte | Pricing and Hedging | Yong Costa | 2002 | Spring | 3.5 | 1
Reyna Sergi | Advanced Computational Modeling in Biology and Biomaterials | Faustino Lawhon | 2015 | Fall | 3.5 | 1
Kia Scheetz | Introduction to Cloud Computing | Hedy Linz | 2013 | Spring | 3.5 | 3
Mabel Lohr | Experimental Design | Jina Haak | 2008 | Spring | 3.5 | 0
Fonda Parkes | Financial Enterprise Risk Engineering | Alyssa Touchstone | 2000 | Summer | 3.5 | 2
Teressa Thornhill | Marketing Analytics | Scotty Burchill | 2002 | Summer | 3.5 | 5
Torie Mcsherry | Database Management Systems I | Gisela Sleeper | 2007 | Summer | 3.5 | 2
Phylicia Raulerson | Database Management Systems I | Gisela Sleeper | 2005 | Fall | 3.5 | 0
Darius Brouwer | Supply Chain Analytics | Yolande Champine | 2000 | Summer | 3.5 | 3
Stephany Mcgranahan | Systems Integration | Ulysses Mcleish | 2008 | Spring | 3.5 | 0
Malinda Troncoso | Data Stream Analytics | Wynell Detrick | 2006 | Fall | 3.5 | 4
Jigar Jain | Advanced Derivatives | Ivan Bodiford | 2004 | Fall | 3.5 | 0
Damion Brady | Special Problems in Financial Engineering | Na Carruth | 2014 | Summer | 3.5 | 4
Samella Scheffel | Risk Management Methods & Applications | Buford Bjerke | 2012 | Summer | 3.5 | 5
Linette Lamagna | Thesis in Financial Engineering | Hyacinth Tebo | 2007 | Summer | 3.5 | 5
Shenika Parson | Pricing and Hedging | Lynwood Gillard | 2013 | Spring | 3.5 | 3
Altagracia Guerrette | Database Management Systems I | Gisela Sleeper | 2008 | Spring | 3.5 | 3
Jack Robin | Data Warehousing and Business Intelligence | Henry Metzger | 2013 | Summer | 3.5 | 2
Cole Mcnichols | Mobile Systems and Applications | Roosevelt Hendren | 2012 | Spring | 3.5 | 5
Anjelica Biscoe | Introduction to Cloud Computing | Hedy Linz | 2008 | Fall | 3.5 | 0
Linette Lamagna | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2014 | Summer | 3.5 | 5
Deb Pietsch | Risk Management Methods & Applications | Buford Bjerke | 2011 | Fall | 3.5 | 4
Quentin Brumsey | Algorithms | Slyvia Elson | 2008 | Summer | 3.5 | 3
Teressa Thornhill | Principles of Programming Languages | Davina Vierling | 2010 | Spring | 3.5 | 2
Karolina Nowak | Supply Chain Analytics | Janice Delph | 2009 | Summer | 3.5 | 0
Jack Robin | Parallel Programming for Many-core Processors | Essie Moorehead | 2002 | Spring | 3.5 | 5
Brian Beesley | Portfolio Theory and Applications | Stephen Tash | 2000 | Spring | 3.5 | 2
Yu Strobl | Portfolio Theory and Applications | Staci Mcdivitt | 2014 | Fall | 3.5 | 0
Torie Mcsherry | Introduction to Programming, Data Structures, and Algorithms | Adah Souder | 2014 | Spring | 3.5 | 3
Terina Strauss | Introduction to Operating Systems | Valentin Witkowski | 2013 | Spring | 3.5 | 1
Liliana Gaitan | Enterprise Software Architecture and Design | Nia Guadalupe | 2002 | Spring | 3.5 | 3
Yun Chen | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2001 | Spring | 3.5 | 3
Elenor Angell | Web Analytics | Consuelo Poche | 2005 | Summer | 3.5 | 1
Melva Basil | Thesis in Financial Engineering | Hyacinth Tebo | 2002 | Fall | 3.5 | 1
Junior Dowdle | Statistical Learning & Analytics | Carita Becenti | 2015 | Fall | 3.5 | 5
Gabriela Kiesling | System Architecture and Design | Maurice Fabry | 2002 | Summer | 3.5 | 1
Shizuko Melton | Introduction to Operating Systems | Blaine Chabot | 2004 | Summer | 3.5 | 3
Derrick Chittenden | Elements of Operations Research | Rachele Wilke | 2005 | Summer | 3.5 | 3
Deb Pietsch | Elements of Operations Research | Jolynn Burkhard | 2008 | Spring | 3.5 | 1
Li Condrey | Mobile Systems and Applications | Melynda Darnell | 2002 | Fall | 3.5 | 3
Li Condrey | Fundamentals of Cybersecurity | Kathlene Lamey | 2011 | Fall | 3.5 | 3
Elenor Angell | Systemic Risk and Financial Regulation | Dyan Jared | 2006 | Summer | 3.5 | 4
Vincenzo Longshore | Artifical Intelligence | Alexandria Rivenburg | 2000 | Summer | 3.5 | 2
Fonda Parkes | Data Warehousing and Business Intelligence | Nicolette Desroches | 2003 | Fall | 3.5 | 4
Mui Choy | Interactive Computer Graphics | Iris Disla | 2001 | Summer | 3.5 | 4
Despina Sires | System Architecture and Design | Rhoda Kearl | 2007 | Spring | 3.5 | 1
Rosella Newcomer | Marketing Analytics | Virgen Quillin | 2013 | Summer | 3.5 | 4
Patricia Remley | Advanced Algorithm Design and Implementation | Vallie Ruse | 2010 | Spring | 3.5 | 1
Anjelica Biscoe | Knowledge Discovery in Databases | Hye Hundt | 2014 | Summer | 3.5 | 4
Jack Robin | Social Network Analytics | Jolynn Burkhard | 2011 | Spring | 3.5 | 0
Keesha Montalbo | Statistical Learning & Analytics | Ellena Bulluck | 2004 | Spring | 3.5 | 0
Jigar Jain | Big Data Seminar | Dori Braaten | 2001 | Fall | 3.5 | 5
Brian Beesley | Algorithms | Juliann Millhouse | 2005 | Spring | 3.5 | 3
Tyson Frix | Privacy in a Networked World | Verna Fee | 2011 | Spring | 3.5 | 2
Tao Feng | Data Warehousing and Business Intelligence | Shanice Harley | 2013 | Spring | 3.5 | 4
Cristine Deming | Stochastic Calculus for Financial Engineers | Chi Krogh | 2004 | Spring | 3.5 | 0
Thi Sylvester | Mobile Systems and Applications | Johnie Shira | 2011 | Summer | 3.5 | 3
Velma Effinger | Social Network Analytics | Jolynn Burkhard | 2011 | Summer | 3.5 | 2
Linette Lamagna | Enterprise Software Architecture and Design | Nia Guadalupe | 2007 | Spring | 3.5 | 3
Mui Choy | Big Data Seminar | Reggie Elser | 2015 | Summer | 3.5 | 1
Fonda Parkes | Distributed and Cloud Computing | Georgine Beaumont | 2010 | Spring | 3.5 | 2
Bonny Pett | Concurrent Programming | Ross Slinkard | 2012 | Summer | 3.5 | 4
Stephany Mcgranahan | Applied Analytics in a World of Big Data | Lacey Payer | 2009 | Summer | 3.5 | 3
Teri Chasse | Fundamentals of Systems Engineering | Eric Maggi | 2000 | Fall | 3.5 | 5
Kendra Salinas | Experimental Design | Rubie Noel | 2001 | Summer | 3.5 | 1
Ka Unsworth | Financial Decision Making | Roger Christon | 2007 | Spring | 3.5 | 0
Suellen Wald | Data Stream Analytics | Florrie Devers | 2001 | Fall | 3.5 | 0
Sterling Krejci | Advanced Computational Modeling in Biology and Biomaterials | Faustino Lawhon | 2001 | Fall | 3.5 | 5
Teressa Thornhill | Social Network Analytics | Benny Mckane | 2009 | Fall | 3.5 | 3
Jack Robin | Risk Management Methods & Applications | Buford Bjerke | 2005 | Summer | 3.5 | 1
Jeromy Maisch | Engineering Economics and Cost Analysis | Analisa Wendell | 2003 | Summer | 3.5 | 2
Blaine Candela | Stochastic Calculus for Financial Engineers | Emelia Minner | 2006 | Fall | 3.5 | 2
Fonda Parkes | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2007 | Summer | 3.5 | 4
Terina Strauss | Introduction to Financial Risk Management | Dawne Aube | 2010 | Summer | 3.5 | 2
Samara Taubman | Parallel Programming for Many-core Processors | Essie Moorehead | 2004 | Spring | 3.5 | 0
So Overturf | Enterprise and Cloud Computing | Mel Kinnear | 2000 | Spring | 3.5 | 5
Anjelica Biscoe | Elements of Operations Research | Ayanna Friel | 2012 | Summer | 3.5 | 2
Dwana Rybicki | Human Computer Interaction | Suzy Rasheed | 2005 | Spring | 3.5 | 4
Despina Sires | Pricing and Hedging | Jodi Croslin | 2007 | Spring | 3.5 | 1
Thi Sylvester | Big Data Seminar | Dori Braaten | 2015 | Summer | 3.5 | 0
Quentin Brumsey | Fundamentals of Cybersecurity | Dalton Sugden | 2001 | Fall | 3.5 | 1
Malinda Troncoso | Data Mining and Knowledge Management | Ofelia Maysonet | 2013 | Spring | 3.5 | 1
Liliana Gaitan | Stochastic Calculus for Financial Engineers | Emelia Minner | 2008 | Summer | 3.5 | 4
Marcella Ostrander | Social Network Analytics | Jolynn Burkhard | 2005 | Summer | 3.5 | 1
Cristine Deming | Statistical Learning & Analytics | Ellena Bulluck | 2015 | Fall | 3.5 | 5
Keyur Doshi | Pricing and Hedging | Yong Costa | 2013 | Summer | 3.5 | 1
Mabel Lohr | Elements of Operations Research | Rachele Wilke | 2005 | Summer | 3.5 | 1
Shenika Parson | Financial Enterprise Risk Engineering | Alyssa Touchstone | 2000 | Summer | 3.5 | 2
Tao Feng | Principles of Programming Languages | Franchesca Almanzar | 2009 | Spring | 3.5 | 2
Elenor Angell | Stochastic Calculus for Financial Engineers | Chi Krogh | 2006 | Fall | 3.5 | 5
Malka Gushiken | Data Warehousing and Business Intelligence | Shanice Harley | 2002 | Fall | 3.5 | 0
Teri Chasse | Computer Organization and Programming | Clifford Mccubbin | 2015 | Summer | 3.5 | 3
John Doe | Distributed and Cloud Computing | Georgine Beaumont | 2003 | Summer | 3.5 | 2
Porsha Rolfes | Strategic Data Management | Shon Montilla | 2010 | Summer | 3.5 | 3
Elenor Angell | Distributed and Cloud Computing | Krysten Devoe | 2010 | Summer | 3.5 | 5
Jack Robin | Elements of Operations Research | Myrtle Newhard | 2014 | Fall | 3.5 | 3
Stephany Mcgranahan | Principles of Programming Languages | Renita Tyus | 2010 | Spring | 3.5 | 3
Malka Gushiken | Advanced Derivatives | Ivan Bodiford | 2005 | Summer | 3.5 | 3
Jc Milburn | Strategic Data Management | Cheyenne Newcombe | 2003 | Fall | 3.5 | 0
Darius Brouwer | Computer Organization and Programming | Joanne Hessling | 2015 | Spring | 3.5 | 1
Shizuko Melton | Strategic Data Management | Cheyenne Newcombe | 2008 | Fall | 3.5 | 0
Keyur Doshi | Parallel Programming for Many-core Processors | Essie Moorehead | 2000 | Fall | 3.5 | 4
Dwana Rybicki | Enterprise and Cloud Computing | Mel Kinnear | 2001 | Spring | 3.5 | 3
Tyson Frix | Applied Analytics in a World of Big Data | Shella Berger | 2006 | Spring | 3.5 | 0
Elenor Angell | Applied Analytics in a World of Big Data | Gaye Busbee | 2006 | Spring | 3.5 | 1
Keesha Montalbo | Multivariate Data Analytics | Nevada Georges | 2006 | Spring | 3.5 | 0
Jeromy Maisch | Introduction to Cloud Computing | Brigette Wenzl | 2007 | Fall | 3.5 | 4
Sue Wilkin | Stochastic Calculus for Financial Engineers | Emelia Minner | 2003 | Fall | 3.5 | 5
Samara Taubman | Social Network Analytics | Jolynn Burkhard | 2001 | Spring | 3.5 | 4
Bruna Lachermeier | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2010 | Summer | 3.5 | 0
Noelle Moll | Special Problems in Financial Engineering | Na Carruth | 2015 | Summer | 3.5 | 4
Keyur Doshi | Statistical Learning & Analytics | Carita Becenti | 2010 | Summer | 3.5 | 1
Junior Dowdle | Stochastic Calculus for Financial Engineers | Emelia Minner | 2002 | Fall | 3.5 | 2
Suellen Wald | Engineering Economics and Cost Analysis | Enoch Cobos | 2003 | Summer | 3.5 | 2
Jigar Jain | Financial Decision Making | Roger Christon | 2013 | Summer | 3.5 | 4
So Overturf | Enterprise Software Architecture and Design | Yolande Pascoe | 2006 | Fall | 3.5 | 1
So Overturf | Social Network Analytics | Jolynn Burkhard | 2013 | Fall | 3.5 | 4
Junior Dowdle | Parallel Programming for Many-core Processors | Essie Moorehead | 2004 | Fall | 3.5 | 3
Teressa Thornhill | Systemic Risk and Financial Regulation | Dyan Jared | 2013 | Summer | 3.5 | 5
Jerome Sharman | Database Management Systems I | Jess Holmes | 2008 | Spring | 3.5 | 5
Malinda Troncoso | Database Management Systems I | Gisela Sleeper | 2005 | Spring | 3.5 | 4
Porsha Rolfes | Fundamentals of Systems Engineering | Eric Maggi | 2005 | Spring | 3.5 | 4
Malinda Troncoso | Fundamentals of Systems Engineering | Antonette Khouri | 2012 | Summer | 3.5 | 3
Sue Wilkin | Computational Methods in Finance | Phoebe Askey | 2005 | Summer | 3.5 | 4
Porsha Rolfes | Pricing and Hedging | Lynwood Gillard | 2011 | Spring | 3.5 | 2
Jenna Sandell | Principles of Programming Languages | Davina Vierling | 2011 | Fall | 3.5 | 3
Tao Feng | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2014 | Fall | 3.5 | 1
Kia Scheetz | Portfolio Theory and Applications | Staci Mcdivitt | 2011 | Fall | 3.5 | 4
Ramiro Sells | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | 2003 | Spring | 3.5 | 0
Bruna Lachermeier | Fundamentals of Cybersecurity | Corey Shue | 2002 | Spring | 3.5 | 2
Randell Werner | Big Data Seminar | Reggie Elser | 2009 | Summer | 3.5 | 2
Malinda Troncoso | Computational Methods in Finance | Rivka Bird | 2008 | Spring | 3.5 | 4
Herschel Doughty | Applied Analytics in a World of Big Data | Shella Berger | 2002 | Spring | 3.5 | 5
Darius Brouwer | Big Data Seminar | Chara Phaneuf | 2009 | Summer | 3.5 | 5
Fonda Parkes | Algorithms | Juliann Millhouse | 2014 | Summer | 3.5 | 1
Quentin Brumsey | Thesis in Financial Engineering | Lorelei Madry | 2004 | Summer | 3.5 | 1
Yu Strobl | Data Stream Analytics | Wynell Detrick | 2001 | Fall | 3.5 | 1
Farah Villafuerte | Concurrent Programming | Ross Slinkard | 2010 | Fall | 3.5 | 3
Bonny Pett | Thesis in Financial Engineering | Hyacinth Tebo | 2012 | Summer | 3.5 | 5
Asley Taff | Fundamentals of Cybersecurity | Kathlene Lamey | 2012 | Fall | 3.5 | 2
Shenika Parson | Advanced Algorithm Design and Implementation | Joie Creech | 2014 | Summer | 3.5 | 5
Jigar Jain | Introduction to Operating Systems | Blaine Chabot | 2010 | Spring | 3.5 | 0
Jia Liu | Engineering Economics and Cost Analysis | Analisa Wendell | 2002 | Spring | 3.5 | 2
Tyson Frix | Fundamentals of Systems Engineering | Eric Maggi | 2010 | Fall | 3.5 | 3
Velma Effinger | Principles of Programming Languages | Davina Vierling | 2011 | Summer | 3.5 | 3
Jc Milburn | Database Management Systems I | Gisela Sleeper | 2000 | Fall | 3.5 | 5
Karolina Nowak | Enterprise and Cloud Computing | Hannelore Spece | 2006 | Fall | 3.5 | 3
Damion Brady | Concurrent Programming | Salley Lex | 2014 | Fall | 3.5 | 3
Li Condrey | Privacy in a Networked World | Connie Thresher | 2008 | Fall | 3.5 | 0
Damion Brady | Computational Methods in Finance | Armando Branch | 2007 | Spring | 3.5 | 0
Classie Elswick | Computer Organization and Programming | Clifford Mccubbin | 2008 | Spring | 3.5 | 1
Malinda Troncoso | Interactive Computer Graphics | Iris Disla | 2010 | Fall | 3.5 | 5
Herschel Doughty | Interactive Computer Graphics | Iris Disla | 2003 | Fall | 3.5 | 4
Phylicia Raulerson | Web Analytics | Margert Ferguson | 2011 | Summer | 3.5 | 2
Jc Milburn | Web Programming | Trent Petrillo | 2010 | Fall | 3.5 | 4
Janita Banaszak | Data Warehousing and Business Intelligence | Henry Metzger | 2009 | Summer | 3.5 | 3
Yu Strobl | Financial Decision Making | Brandy Neth | 2012 | Fall | 3.5 | 1
Quincy Prisco | Financial Enterprise Risk Engineering | Kurt Shimek | 2014 | Fall | 3.5 | 4
Shenika Parson | Computer Organization and Programming | Joanne Hessling | 2015 | Fall | 3.5 | 2
Sana Manion | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2011 | Fall | 3.5 | 2
Li Condrey | Project Management of Complex Systems | Leena Spradley | 2006 | Summer | 3.5 | 1
Pei Nagel | Web Programming | Erica Thoman | 2012 | Summer | 3.5 | 0
Tamica Fauntleroy | Introduction to Cloud Computing | Hedy Linz | 2015 | Summer | 3.5 | 0
Darius Brouwer | Fundamentals of Cybersecurity | Corey Shue | 2002 | Fall | 3.5 | 4
Jia Liu | Special Problems in Financial Engineering | Na Carruth | 2014 | Spring | 3.5 | 1
Shizuko Melton | Parallel Programming for Many-core Processors | Marline Kamel | 2000 | Summer | 3.5 | 0
Quincy Prisco | Pricing and Hedging | Jodi Croslin | 2001 | Spring | 3.5 | 2
Derrick Chittenden | Portfolio Theory and Applications | Rea Schlatter | 2015 | Summer | 3.5 | 2
Samara Taubman | Pricing and Hedging | Jodi Croslin | 2006 | Fall | 3.5 | 3
Phylicia Raulerson | TCP/IP Networking | Tyler Fout | 2015 | Spring | 3.5 | 1
Alvaro Legrande | Fundamentals of Systems Engineering | Edris Poff | 2007 | Spring | 3.5 | 5
Noelle Moll | Risk Management Methods & Applications | Katie Mattison | 2012 | Spring | 3.5 | 2
Gabriela Kiesling | Financial Decision Making | Marquetta Claude | 2004 | Spring | 3.5 | 3
Vincenzo Longshore | Big Data Seminar | Chara Phaneuf | 2005 | Fall | 3.5 | 5
Anuj Batra | Engineering Economics and Cost Analysis | Kaycee Whitford | 2007 | Fall | 3.5 | 3
Tyson Frix | Database Management Systems I | Gisela Sleeper | 2006 | Summer | 3.5 | 1
Ka Unsworth | Portfolio Theory and Applications | Staci Mcdivitt | 2000 | Summer | 3.5 | 4
Junior Dowdle | Multivariate Data Analytics | Nevada Georges | 2002 | Fall | 3.5 | 1
Herschel Doughty | Web Analytics | Margert Ferguson | 2011 | Summer | 3.5 | 3
Mui Choy | Portfolio Theory and Applications | Rea Schlatter | 2001 | Spring | 3.5 | 2
Jenna Sandell | Data Mining and Knowledge Management | Ofelia Maysonet | 2002 | Spring | 3.5 | 4
Jack Robin | Introduction to Programming, Data Structures, and Algorithms | Adah Souder | 2002 | Fall | 3.5 | 1
Bonny Pett | Mobile Systems and Applications | Roosevelt Hendren | 2008 | Fall | 3.5 | 5
Reyna Sergi | Experimental Design | Jina Haak | 2010 | Summer | 3.5 | 2
Sana Manion | Web Analytics | Margert Ferguson | 2002 | Fall | 3.5 | 5
Romona Mishoe | Web Programming | Trent Petrillo | 2013 | Fall | 3.5 | 0
Kyra Stecklein | Introduction to Programming, Data Structures, and Algorithms | Basilia Pendergrast | 2005 | Summer | 3.5 | 5
Terina Strauss | Systems Integration | Shaunta Bergman | 2009 | Summer | 3.5 | 5
Bonny Pett | Web Programming | Trent Petrillo | 2001 | Summer | 3.5 | 5
Deb Pietsch | Enterprise Software Architecture and Design | Nia Guadalupe | 2003 | Spring | 3.5 | 3
Li Condrey | Engineering Economics and Cost Analysis | Enoch Cobos | 2010 | Fall | 3.5 | 3
Kenyetta Troutman | Portfolio Theory and Applications | Stephen Tash | 2008 | Fall | 3.5 | 1
Anuj Batra | Computer Organization and Programming | Joanne Hessling | 2003 | Spring | 3.5 | 4
Jia Liu | Introduction to Cloud Computing | Brigette Wenzl | 2004 | Fall | 3.5 | 3
Danica Tarin | Elements of Operations Research | Myrtle Newhard | 2007 | Fall | 3.5 | 0
Danica Tarin | Parallel Programming for Many-core Processors | Demetra Krein | 2004 | Summer | 3.5 | 3
Sue Wilkin | Introduction to Cloud Computing | Hedy Linz | 2007 | Summer | 3.5 | 5
Darius Brouwer | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2003 | Spring | 3.5 | 1
Keesha Montalbo | Human Computer Interaction | Kathlyn Murphey | 2004 | Spring | 3.5 | 1
Cristine Deming | Introduction to Programming, Data Structures, and Algorithms | Basilia Pendergrast | 2004 | Summer | 3.5 | 4
Malinda Troncoso | Multivariate Data Analytics | Nevada Georges | 2008 | Fall | 3.5 | 5
Ajai Thomas | Project Management of Complex Systems | Birgit Swager | 2011 | Fall | 3.5 | 2
Patricia Remley | Special Problems in Financial Engineering | Roslyn Matz | 2000 | Fall | 3.5 | 3
Randell Werner | Introduction to Financial Risk Management | Raguel Shugart | 2011 | Summer | 3.5 | 3
Herschel Doughty | Marketing Analytics | Bruna Gibbs | 2006 | Spring | 3.5 | 1
Samella Scheffel | Interactive Computer Graphics | Lauran Okelley | 2014 | Spring | 3.5 | 2
Cristine Deming | Enterprise and Cloud Computing | Hannelore Spece | 2008 | Fall | 3.5 | 5
Mui Choy | Engineering Economics and Cost Analysis | Kaycee Whitford | 2005 | Summer | 3.5 | 0
Fonda Parkes | Web Programming | Milo Hitchman | 2000 | Spring | 3.5 | 1
Anjelica Biscoe | Statistical Learning & Analytics | Carita Becenti | 2005 | Fall | 3.5 | 3
Herschel Doughty | Portfolio Theory and Applications | Rea Schlatter | 2011 | Spring | 3.5 | 0
Derrick Chittenden | Fundamentals of Cybersecurity | Dalton Sugden | 2008 | Fall | 3.5 | 5
Velma Effinger | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | 2015 | Fall | 3.5 | 3
Yu Strobl | Web Programming | Trent Petrillo | 2006 | Summer | 3.5 | 5
Johnsie Devaughn | Supply Chain Analytics | Yoshiko Derrickson | 2005 | Spring | 3.5 | 0
Randell Werner | Human Computer Interaction | Deb Birkland | 2009 | Spring | 3.5 | 5
Damion Brady | Applied Analytics in a World of Big Data | Lacey Payer | 2006 | Spring | 3.5 | 4
Phylicia Raulerson | Financial Decision Making | Roger Christon | 2001 | Summer | 3.5 | 3
Alvaro Legrande | Strategic Data Management | Randolph Lundell | 2011 | Summer | 3.5 | 5
Jia Liu | Artifical Intelligence | Alexandria Rivenburg | 2014 | Fall | 3.5 | 2
Elenor Angell | Data Warehousing and Business Intelligence | Henry Metzger | 2009 | Summer | 3.5 | 3
Stephany Mcgranahan | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2001 | Summer | 3.5 | 0
Yu Strobl | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2014 | Summer | 3.5 | 3
Shenika Parson | Portfolio Theory and Applications | Rea Schlatter | 2000 | Summer | 3.5 | 1
Keesha Montalbo | Strategic Data Management | Cheyenne Newcombe | 2010 | Spring | 3.5 | 4
Jigar Jain | Engineering Economics and Cost Analysis | Kaycee Whitford | 2013 | Spring | 3.5 | 4
Samara Taubman | TCP/IP Networking | Ashlea Currie | 2014 | Fall | 3.5 | 5
Teressa Thornhill | Strategic Data Management | Cheyenne Newcombe | 2007 | Summer | 3.5 | 3
Jian Tang | Elements of Operations Research | Rachele Wilke | 2006 | Fall | 3.5 | 4
Junior Dowdle | Experimental Design | Rubie Noel | 2014 | Summer | 3.5 | 0
Quentin Brumsey | Statistical Learning & Analytics | Ellena Bulluck | 2005 | Summer | 3.5 | 3
Cristine Deming | Supply Chain Analytics | Yoshiko Derrickson | 2006 | Summer | 3.5 | 1
Jack Robin | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | 2002 | Spring | 3.5 | 0
Cole Mcnichols | Stochastic Calculus for Financial Engineers | Emelia Minner | 2001 | Summer | 3.5 | 1
Lauri Lundeen | Computational Methods in Finance | Rivka Bird | 2010 | Spring | 3.5 | 2
Tobi Dantin | Computational Methods in Finance | Rivka Bird | 2012 | Summer | 3.5 | 3
Kyra Stecklein | Optimization and Process Analytics | Kaycee Valla | 2012 | Fall | 3.5 | 5
Phylicia Raulerson | Pricing and Hedging | Jodi Croslin | 2010 | Fall | 3.5 | 3
Keesha Montalbo | Pricing and Hedging | Yong Costa | 2002 | Fall | 3.5 | 0
Samella Scheffel | Knowledge Discovery in Databases | Alexandria Hollon | 2006 | Summer | 3.5 | 5
Romona Mishoe | Advanced Derivatives | Ivan Bodiford | 2007 | Spring | 3.5 | 5
Sterling Krejci | Algorithms | Slyvia Elson | 2003 | Summer | 3.5 | 2
Anjelica Biscoe | Portfolio Theory and Applications | Stephen Tash | 2004 | Spring | 3.5 | 1
Velma Effinger | Computer Organization and Programming | Joanne Hessling | 2001 | Fall | 3.5 | 4
Darius Brouwer | Data Warehousing and Business Intelligence | Henry Metzger | 2001 | Spring | 3.5 | 4
Despina Sires | Introduction to Operating Systems | Blaine Chabot | 2011 | Summer | 3.5 | 0
Kia Scheetz | Parallel Programming for Many-core Processors | Demetra Krein | 2010 | Fall | 3.5 | 0
Terina Strauss | Privacy in a Networked World | Jesusita Dittman | 2014 | Summer | 3.5 | 5
Jeromy Maisch | Human Computer Interaction | Deb Birkland | 2014 | Summer | 3.5 | 3
Kendra Salinas | Introduction to Financial Risk Management | Kerstin Sickler | 2008 | Fall | 3.5 | 5
Gabriela Kiesling | Financial Enterprise Risk Engineering | Kurt Shimek | 2013 | Summer | 3.5 | 3
Stephany Mcgranahan | Financial Decision Making | Brandy Neth | 2011 | Fall | 3.5 | 2
Suellen Wald | Financial Decision Making | Roger Christon | 2002 | Summer | 3.5 | 1
Derrick Chittenden | Enterprise and Cloud Computing | Linsey Rosen | 2011 | Fall | 3.5 | 3
Darius Brouwer | Distributed and Cloud Computing | Esperanza Frahm | 2013 | Spring | 3.5 | 2
Cristine Deming | Stochastic Calculus for Financial Engineers | Chi Krogh | 2005 | Summer | 3.5 | 5
Teressa Thornhill | Artifical Intelligence | Joanie Rotella | 2006 | Fall | 3.5 | 4
Janita Banaszak | Applied Analytics in a World of Big Data | Shella Berger | 2002 | Fall | 3.5 | 1
Cristine Deming | Advanced Derivatives | Pearle Steffensen | 2003 | Summer | 3.5 | 2
Page Mell | Experimental Design | Elli Cornman | 2003 | Summer | 3.5 | 4
Mui Choy | Data Mining and Knowledge Management | Romana Waddington | 2001 | Spring | 3.5 | 2
Kenyetta Troutman | Privacy in a Networked World | Connie Thresher | 2011 | Summer | 3.5 | 3
Malinda Troncoso | Experimental Design | Rubie Noel | 2010 | Spring | 3.5 | 3
Effie Endicott | Web Analytics | Crissy Weidman | 2000 | Fall | 3.5 | 0
Karolina Nowak | Portfolio Theory and Applications | Rea Schlatter | 2005 | Spring | 3.5 | 3
Sana Manion | Supply Chain Analytics | Yoshiko Derrickson | 2002 | Spring | 3.5 | 2
Porsha Rolfes | Supply Chain Analytics | Janice Delph | 2012 | Spring | 3.5 | 5
Malinda Troncoso | Human Computer Interaction | Suzy Rasheed | 2014 | Fall | 3.5 | 0
Tobi Dantin | Elements of Operations Research | Ayanna Friel | 2004 | Spring | 3.5 | 1
Danica Tarin | Computational Methods in Finance | Phoebe Askey | 2000 | Fall | 3.5 | 5
Pei Nagel | Enterprise Software Architecture and Design | Rikki Tarry | 2007 | Summer | 3.5 | 1
Kyra Stecklein | Parallel Programming for Many-core Processors | Marline Kamel | 2009 | Fall | 3.5 | 1
Malinda Troncoso | Computer Organization and Programming | Clifford Mccubbin | 2007 | Summer | 3.5 | 3
Reyna Sergi | Introduction to Programming, Data Structures, and Algorithms | Basilia Pendergrast | 2015 | Spring | 3.5 | 1
Brian Beesley | Computer Organization and Programming | Joanne Hessling | 2007 | Summer | 3.5 | 5
Rosella Newcomer | Fundamentals of Cybersecurity | Kathlene Lamey | 2009 | Fall | 3.5 | 4
Brandee Ferrier | Web Programming | Milo Hitchman | 2014 | Spring | 3.5 | 4
Julianne Korb | Supply Chain Analytics | Yolande Champine | 2002 | Fall | 3.5 | 5
Farah Villafuerte | Algorithms | Juliann Millhouse | 2000 | Summer | 3.5 | 0
Junior Dowdle | Optimization and Process Analytics | Fredricka Fontanez | 2003 | Fall | 3.5 | 3
Yu Strobl | Special Problems in Financial Engineering | Na Carruth | 2003 | Spring | 3.5 | 4
Anuj Batra | Web Programming | Erica Thoman | 2013 | Fall | 3.5 | 4
Porsha Rolfes | Stochastic Calculus for Financial Engineers | Chi Krogh | 2014 | Spring | 3.5 | 2
Keyur Doshi | Special Problems in Financial Engineering | Linwood Tryon | 2002 | Spring | 3.5 | 1
Jeromy Maisch | Data Stream Analytics | Wynell Detrick | 2015 | Fall | 3.5 | 0
Deb Pietsch | Advanced Derivatives | Ivan Bodiford | 2011 | Summer | 3.5 | 1
Elenor Angell | Database Management Systems I | Gisela Sleeper | 2015 | Spring | 3.5 | 0
Altagracia Guerrette | Fundamentals of Cybersecurity | Corey Shue | 2011 | Fall | 3.5 | 5
Reyna Sergi | Artifical Intelligence | Iliana Nicoletti | 2014 | Fall | 3.5 | 0
Effie Endicott | Thesis in Financial Engineering | Hyacinth Tebo | 2003 | Summer | 3.5 | 4
Yu Strobl | Pricing and Hedging | Yong Costa | 2014 | Summer | 3.5 | 0
Farah Villafuerte | Social Network Analytics | Jolynn Burkhard | 2000 | Summer | 3.5 | 1
Jc Milburn | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | 2002 | Spring | 3.5 | 0
Torie Mcsherry | Thesis in Financial Engineering | Hyacinth Tebo | 2015 | Summer | 3.5 | 1
Cole Mcnichols | TCP/IP Networking | Tyler Fout | 2006 | Spring | 3.5 | 2
Sue Wilkin | Marketing Analytics | Scotty Burchill | 2012 | Fall | 3.5 | 3
Jc Milburn | Marketing Analytics | Virgen Quillin | 2006 | Spring | 3.5 | 2
Darius Brouwer | Enterprise and Cloud Computing | Hannelore Spece | 2004 | Spring | 3.5 | 4
Johnsie Devaughn | Optimization and Process Analytics | Fredricka Fontanez | 2000 | Spring | 3.5 | 2
Jenna Sandell | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2000 | Summer | 3.5 | 0
Quincy Prisco | Statistical Learning & Analytics | Carita Becenti | 2014 | Fall | 3.5 | 1
Hisako Crumbley | Privacy in a Networked World | Jesusita Dittman | 2008 | Spring | 3.5 | 5
Tao Feng | Parallel Programming for Many-core Processors | Marline Kamel | 2000 | Summer | 3.5 | 4
Rosella Newcomer | Statistical Learning & Analytics | Ray Outlaw | 2010 | Spring | 3.5 | 3
Cole Mcnichols | Artifical Intelligence | Iliana Nicoletti | 2009 | Fall | 3.5 | 0
Ettie Lubinsky | Stochastic Calculus for Financial Engineers | Chi Krogh | 2005 | Spring | 3.5 | 2
Asley Taff | Experimental Design | Rubie Noel | 2007 | Spring | 3.5 | 2
Cristine Deming | Parallel Programming for Many-core Processors | Demetra Krein | 2005 | Summer | 3.5 | 0
Herschel Doughty | Systemic Risk and Financial Regulation | Thurman Haakenson | 2000 | Spring | 3.5 | 5
Quincy Prisco | Project Management of Complex Systems | Birgit Swager | 2012 | Fall | 3.5 | 0
Samara Taubman | Risk Management Methods & Applications | Buford Bjerke | 2014 | Summer | 3.5 | 0
Altagracia Guerrette | Optimization and Process Analytics | Kaycee Valla | 2006 | Fall | 3.5 | 2
Jenna Sandell | Data Stream Analytics | Wynell Detrick | 2010 | Summer | 3.5 | 1
Shonda Mccarter | Knowledge Discovery in Databases | Alexandria Hollon | 2001 | Fall | 3.5 | 5
Keesha Montalbo | Marketing Analytics | Scotty Burchill | 2009 | Spring | 3.5 | 1
Noelle Moll | Multivariate Data Analytics | Nevada Georges | 2001 | Fall | 3.5 | 5
Damion Brady | Enterprise and Cloud Computing | Hannelore Spece | 2002 | Spring | 3.5 | 3
Pei Nagel | Algorithms | Slyvia Elson | 2013 | Summer | 3.5 | 1
Terina Strauss | Applied Analytics in a World of Big Data | Lacey Payer | 2001 | Summer | 3.5 | 0
Farah Villafuerte | Fundamentals of Systems Engineering | Edris Poff | 2003 | Spring | 3.5 | 1
Yu Strobl | Big Data Seminar | Dori Braaten | 2003 | Spring | 3.5 | 2
Herschel Doughty | Optimization and Process Analytics | Fredricka Fontanez | 2013 | Spring | 3.5 | 1
Patricia Remley | Portfolio Theory and Applications | Stephen Tash | 2015 | Summer | 3.5 | 4
Yu Strobl | Marketing Analytics | Scotty Burchill | 2011 | Summer | 3.5 | 1
Adria Clickner | Parallel Programming for Many-core Processors | Marline Kamel | 2008 | Fall | 3.5 | 0
Jenna Sandell | Systems Integration | Shaunta Bergman | 2004 | Fall | 3.5 | 1
Damion Brady | Financial Enterprise Risk Engineering | Kurt Shimek | 2003 | Summer | 3.5 | 2
Fonda Parkes | Pricing and Hedging | Lynwood Gillard | 2013 | Spring | 3.5 | 2
Vincenzo Longshore | Algorithms | Juliann Millhouse | 2000 | Spring | 3.5 | 4
Keesha Montalbo | Distributed and Cloud Computing | Esperanza Frahm | 2010 | Summer | 3.5 | 3
Tobi Dantin | TCP/IP Networking | Jeanice Papadopoulos | 2007 | Fall | 3.5 | 5
Effie Endicott | Knowledge Discovery in Databases | Alexandria Hollon | 2010 | Summer | 3.5 | 0
Karolina Nowak | Data Mining and Knowledge Management | Ofelia Maysonet | 2012 | Fall | 3.5 | 4
Page Mell | Fundamentals of Cybersecurity | Dalton Sugden | 2000 | Fall | 3.5 | 3
Yun Chen | Marketing Analytics | Scotty Burchill | 2012 | Fall | 3.5 | 4
Terina Strauss | Advanced Computational Modeling in Biology and Biomaterials | Faustino Lawhon | 2010 | Spring | 3.5 | 0
Romona Mishoe | Special Problems in Financial Engineering | Linwood Tryon | 2000 | Fall | 3.5 | 1
Page Mell | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2011 | Spring | 3.5 | 5
Teri Chasse | Elements of Operations Research | Rachele Wilke | 2015 | Spring | 3.5 | 1
Alvaro Legrande | Thesis in Financial Engineering | Lorelei Madry | 2007 | Fall | 3.5 | 1
Classie Elswick | Algorithms | Slyvia Elson | 2004 | Fall | 3.5 | 2
Jc Milburn | Web Analytics | Margert Ferguson | 2009 | Spring | 3.5 | 0
Patricia Remley | Artifical Intelligence | Iliana Nicoletti | 2001 | Fall | 3.5 | 0
Quincy Prisco | Enterprise Software Architecture and Design | Yolande Pascoe | 2013 | Fall | 3.5 | 1
Danica Tarin | Data Mining and Knowledge Management | Ofelia Maysonet | 2015 | Spring | 3.5 | 0
Altagracia Guerrette | TCP/IP Networking | Tyler Fout | 2003 | Summer | 3.5 | 5
Quentin Brumsey | System Architecture and Design | Rhoda Kearl | 2004 | Spring | 3.5 | 2
Cole Mcnichols | Engineering Economics and Cost Analysis | Analisa Wendell | 2007 | Summer | 3.5 | 0
Linette Lamagna | Interactive Computer Graphics | Lauran Okelley | 2004 | Fall | 3.5 | 4
Velma Effinger | Introduction to Financial Risk Management | Raguel Shugart | 2000 | Summer | 3.5 | 3
Krystyna Yaple | Applied Analytics in a World of Big Data | Gaye Busbee | 2013 | Summer | 3.5 | 0
Noelle Moll | Optimization and Process Analytics | Fredricka Fontanez | 2009 | Fall | 3.5 | 1
Gabriela Kiesling | Systemic Risk and Financial Regulation | Pearle Mcphatter | 2003 | Spring | 3.5 | 1
Romona Mishoe | Data Warehousing and Business Intelligence | Henry Metzger | 2010 | Spring | 3.5 | 4
Sana Manion | Advanced Derivatives | Ivan Bodiford | 2010 | Spring | 3.5 | 0
Mabel Lohr | Pricing and Hedging | Jodi Croslin | 2002 | Summer | 3.5 | 1
Anjelica Biscoe | Optimization and Process Analytics | Kaycee Valla | 2007 | Summer | 3.5 | 5
Sana Manion | Portfolio Theory and Applications | Staci Mcdivitt | 2013 | Spring | 3.5 | 5
Jenna Sandell | Enterprise Software Architecture and Design | Yolande Pascoe | 2006 | Fall | 3.5 | 5
Cristine Deming | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | 2011 | Fall | 3.5 | 0
Anjelica Biscoe | Engineering Economics and Cost Analysis | Enoch Cobos | 2003 | Fall | 3.5 | 1
Mui Choy | Financial Enterprise Risk Engineering | Burton Bad | 2005 | Spring | 3.5 | 1
Mui Choy | Project Management of Complex Systems | Leena Spradley | 2008 | Summer | 3.5 | 4
So Overturf | Algorithms | Juliann Millhouse | 2010 | Summer | 3.5 | 2
Effie Endicott | Applied Analytics in a World of Big Data | Shella Berger | 2012 | Fall | 3.5 | 1
Despina Sires | Optimization and Process Analytics | Fredricka Fontanez | 2012 | Spring | 3.5 | 3
Yu Strobl | Web Analytics | Margert Ferguson | 2009 | Fall | 3.5 | 0
Teri Chasse | Special Problems in Financial Engineering | Roslyn Matz | 2011 | Summer | 3.5 | 5
Shonda Mccarter | Enterprise and Cloud Computing | Mel Kinnear | 2014 | Spring | 3.5 | 1
Dwana Rybicki | Social Network Analytics | Shaunte Bischof | 2003 | Summer | 3.5 | 1
Brandee Ferrier | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2015 | Fall | 3.5 | 5
Velma Effinger | Pricing and Hedging | Jodi Croslin | 2005 | Fall | 3.5 | 3
Jigar Jain | Human Computer Interaction | Deb Birkland | 2013 | Fall | 3.5 | 4
Jetta Hinkley | Marketing Analytics | Bruna Gibbs | 2015 | Spring | 3.5 | 2
Jerome Sharman | Mobile Systems and Applications | Johnie Shira | 2007 | Spring | 3.5 | 1
Ettie Lubinsky | Introduction to Cloud Computing | Brigette Wenzl | 2013 | Summer | 3.5 | 5
Jack Robin | Advanced Derivatives | Pearle Steffensen | 2009 | Summer | 3.5 | 3
Elenor Angell | Introduction to Operating Systems | Blaine Chabot | 2006 | Spring | 3.5 | 2
Linette Lamagna | Human Computer Interaction | Deb Birkland | 2004 | Summer | 3.5 | 4
Addie Gin | Advanced Derivatives | Elinore Nye | 2014 | Summer | 3.5 | 4
Malinda Troncoso | Introduction to Programming, Data Structures, and Algorithms | Basilia Pendergrast | 2000 | Spring | 3.5 | 4
Deb Pietsch | Distributed and Cloud Computing | Krysten Devoe | 2003 | Fall | 3.5 | 2
Pei Nagel | Pricing and Hedging | Jodi Croslin | 2011 | Spring | 3.5 | 5
Cole Mcnichols | Advanced Algorithm Design and Implementation | Joie Creech | 2009 | Fall | 3.5 | 0
Tyson Frix | Knowledge Discovery in Databases | Demetria Bradfield | 2009 | Spring | 3.5 | 3
Jc Milburn | Social Network Analytics | Benny Mckane | 2007 | Spring | 3.5 | 4
Linette Lamagna | Multivariate Data Analytics | Nevada Georges | 2011 | Fall | 3.5 | 5
Romona Mishoe | Fundamentals of Cybersecurity | Corey Shue | 2006 | Fall | 3.5 | 2
Adria Clickner | Optimization and Process Analytics | Buddy Maughan | 2006 | Spring | 3.5 | 1
Reyna Sergi | Advanced Derivatives | Elinore Nye | 2011 | Summer | 3.5 | 1
Keesha Montalbo | System Architecture and Design | Isa Serrata | 2003 | Fall | 3.5 | 1
Kendra Salinas | Human Computer Interaction | Kathlyn Murphey | 2006 | Spring | 3.5 | 1
Romona Mishoe | Pricing and Hedging | Yong Costa | 2002 | Fall | 3.5 | 5
Melva Basil | Supply Chain Analytics | Janice Delph | 2010 | Spring | 3.5 | 0
Yu Strobl | Computer Organization and Programming | Joanne Hessling | 2001 | Spring | 3.5 | 0
Noelle Moll | System Architecture and Design | Maurice Fabry | 2010 | Spring | 3.5 | 1
Hisako Crumbley | Enterprise and Cloud Computing | Linsey Rosen | 2000 | Summer | 3.5 | 4
Romona Mishoe | Optimization and Process Analytics | Fredricka Fontanez | 2010 | Summer | 3.5 | 5
Asley Taff | Optimization and Process Analytics | Kaycee Valla | 2013 | Summer | 3.5 | 1
Ajai Thomas | Concurrent Programming | Imelda Palm | 2015 | Spring | 3.5 | 2
Asley Taff | Introduction to Programming, Data Structures, and Algorithms | Tiffanie Rome | 2001 | Spring | 3.5 | 1
Jack Robin | Data Stream Analytics | Adrien Duggins | 2006 | Summer | 3.5 | 4
Shonda Mccarter | Engineering Economics and Cost Analysis | Kaycee Whitford | 2001 | Summer | 3.5 | 2
Teressa Thornhill | Concurrent Programming | Ross Slinkard | 2012 | Fall | 3.5 | 3
Suellen Wald | Experimental Design | Elli Cornman | 2004 | Fall | 3.5 | 5
Marcella Ostrander | Introduction to Financial Risk Management | Dawne Aube | 2005 | Summer | 3.5 | 5
Brandee Ferrier | Data Warehousing and Business Intelligence | Henry Metzger | 2006 | Fall | 3.5 | 5
Kyra Stecklein | Introduction to Operating Systems | Valentin Witkowski | 2008 | Spring | 3.5 | 2
Pei Nagel | Fundamentals of Systems Engineering | Edris Poff | 2015 | Fall | 3.5 | 5
Kendra Salinas | Systems Integration | Sean Tremblay | 2008 | Fall | 3.5 | 4
Jetta Hinkley | Mobile Systems and Applications | Melynda Darnell | 2009 | Fall | 3.5 | 4
Johnsie Devaughn | Engineering Economics and Cost Analysis | Enoch Cobos | 2014 | Summer | 3.5 | 4
Cristine Deming | Financial Enterprise Risk Engineering | Kurt Shimek | 2015 | Spring | 3.5 | 0
Krystyna Yaple | Marketing Analytics | Virgen Quillin | 2014 | Fall | 3.5 | 3
Ajai Thomas | Advanced Computational Modeling in Biology and Biomaterials | Faustino Lawhon | 2005 | Spring | 3.5 | 4
Thi Sylvester | Financial Decision Making | Brandy Neth | 2013 | Spring | 3.5 | 0
Krystyna Yaple | System Architecture and Design | Maurice Fabry | 2013 | Fall | 3.5 | 5
Jenna Sandell | Systemic Risk and Financial Regulation | Thurman Haakenson | 2013 | Spring | 3.5 | 0
Adria Clickner | Concurrent Programming | Ross Slinkard | 2013 | Spring | 3.5 | 5
Adria Clickner | Applied Analytics in a World of Big Data | Gaye Busbee | 2010 | Spring | 3.5 | 2
Lauri Lundeen | Fundamentals of Cybersecurity | Dalton Sugden | 2011 | Spring | 3.5 | 3
Elenor Angell | Experimental Design | Jina Haak | 2012 | Spring | 3.5 | 3
Tao Feng | Interactive Computer Graphics | Iris Disla | 2006 | Spring | 3.5 | 0
Cristine Deming | Principles of Programming Languages | Davina Vierling | 2015 | Summer | 3.5 | 4
Dwana Rybicki | Computational Methods in Finance | Armando Branch | 2000 | Fall | 3.5 | 4
Quincy Prisco | Financial Decision Making | Brandy Neth | 2015 | Spring | 3.5 | 4
Mui Choy | Thesis in Financial Engineering | Lovella Bash | 2001 | Summer | 3.5 | 3
Alvaro Legrande | Pricing and Hedging | Yong Costa | 2008 | Summer | 3.5 | 1
Krystyna Yaple | Fundamentals of Cybersecurity | Kathlene Lamey | 2000 | Summer | 3.5 | 1
Elenor Angell | Optimization and Process Analytics | Fredricka Fontanez | 2013 | Fall | 3.5 | 1
Deb Pietsch | Parallel Programming for Many-core Processors | Demetra Krein | 2014 | Spring | 3.5 | 2
Mui Choy | Data Warehousing and Business Intelligence | Henry Metzger | 2015 | Fall | 3.5 | 3
Malka Gushiken | Enterprise Software Architecture and Design | Yolande Pascoe | 2006 | Fall | 3.5 | 1
Danica Tarin | Applied Analytics in a World of Big Data | Shella Berger | 2015 | Summer | 3.5 | 2
Tobi Dantin | Special Problems in Financial Engineering | Na Carruth | 2009 | Fall | 3.5 | 3
Krystyna Yaple | Human Computer Interaction | Suzy Rasheed | 2015 | Spring | 3.5 | 5
Krystyna Yaple | Algorithms | Juliann Millhouse | 2011 | Spring | 3.5 | 4
Samella Scheffel | Mobile Systems and Applications | Melynda Darnell | 2012 | Spring | 3.5 | 2
Karolina Nowak | Advanced Derivatives | Ivan Bodiford | 2003 | Spring | 3.5 | 4
Rosella Newcomer | Strategic Data Management | Randolph Lundell | 2012 | Fall | 3.5 | 5
Noelle Moll | Pricing and Hedging | Jodi Croslin | 2012 | Spring | 3.5 | 2
Ettie Lubinsky | Portfolio Theory and Applications | Rea Schlatter | 2013 | Fall | 3.5 | 1
Despina Sires | Enterprise Software Architecture and Design | Nia Guadalupe | 2005 | Fall | 3.5 | 3
Kenyetta Troutman | Fundamentals of Cybersecurity | Dalton Sugden | 2005 | Fall | 3.5 | 3
Cole Mcnichols | Parallel Programming for Many-core Processors | Marline Kamel | 2014 | Fall | 3.5 | 2
Quentin Brumsey | Parallel Programming for Many-core Processors | Essie Moorehead | 2014 | Fall | 3.5 | 3
Junior Dowdle | Portfolio Theory and Applications | Rea Schlatter | 2005 | Summer | 3.5 | 0
Jigar Jain | Stochastic Calculus for Financial Engineers | Crissy Bazan | 2005 | Fall | 3.5 | 5
Suellen Wald | Portfolio Theory and Applications | Staci Mcdivitt | 2001 | Spring | 3.5 | 0
Li Condrey | Principles of Programming Languages | Franchesca Almanzar | 2015 | Fall | 3.5 | 1
Stephany Mcgranahan | Project Management of Complex Systems | Birgit Swager | 2013 | Fall | 3.5 | 1
Kia Scheetz | Thesis in Financial Engineering | Lorelei Madry | 2009 | Summer | 3.5 | 3
Asley Taff | Parallel Programming for Many-core Processors | Demetra Krein | 2010 | Summer | 3.5 | 3
Teressa Thornhill | Data Warehousing and Business Intelligence | Shanice Harley | 2001 | Spring | 3.5 | 3
Jian Tang | TCP/IP Networking | Ashlea Currie | 2015 | Spring | 3.5 | 3
Shizuko Melton | Introduction to Cloud Computing | Hedy Linz | 2011 | Fall | 3.5 | 5
Tao Feng | Marketing Analytics | Scotty Burchill | 2007 | Spring | 3.5 | 0
Bonny Pett | Engineering Economics and Cost Analysis | Kaycee Whitford | 2010 | Fall | 3.5 | 0
Samara Taubman | Knowledge Discovery in Databases | Alexandria Hollon | 2011 | Summer | 3.5 | 4
Krystyna Yaple | System Architecture and Design | Maurice Fabry | 2005 | Summer | 3.5 | 0
Ettie Lubinsky | Experimental Design | Jina Haak | 2011 | Summer | 3.5 | 4
Shenika Parson | Database Management Systems I | Jess Holmes | 2011 | Summer | 3.5 | 3
Dwana Rybicki | Stochastic Calculus for Financial Engineers | Chi Krogh | 2003 | Summer | 3.5 | 5
Hisako Crumbley | Data Warehousing and Business Intelligence | Shanice Harley | 2011 | Spring | 3.5 | 0
Sue Wilkin | Social Network Analytics | Jolynn Burkhard | 2002 | Fall | 3.5 | 5
Ettie Lubinsky | Social Network Analytics | Benny Mckane | 2002 | Fall | 3.5 | 3
Despina Sires | Mobile Systems and Applications | Roosevelt Hendren | 2003 | Fall | 3.5 | 1
Noelle Moll | Distributed and Cloud Computing | Esperanza Frahm | 2011 | Spring | 3.5 | 5
Johnsie Devaughn | Stochastic Calculus for Financial Engineers | Emelia Minner | 2005 | Spring | 3.5 | 5
Jack Robin | Principles of Programming Languages | Franchesca Almanzar | 2007 | Summer | 3.5 | 0
Marcella Ostrander | Strategic Data Management | Shon Montilla | 2015 | Spring | 3.5 | 2
Sana Manion | Enterprise Software Architecture and Design | Yolande Pascoe | 2001 | Fall | 3.5 | 4
Malka Gushiken | Data Mining and Knowledge Management | Shauna Ornelas | 2001 | Summer | 3.5 | 1

## Testing
Student Name | Course Name | Course Rating
Mabel Lohr | Advanced Algorithm Design and Implementation | 3.5
Pei Nagel | Introduction to Financial Risk Management | 1.5
Cristine Deming | Introduction to Financial Risk Management | 2.5
Effie Endicott | Data Warehousing and Business Intelligence | 3.5
Shonda Mccarter | Risk Management Methods & Applications | 3.5
Janita Banaszak | Strategic Data Management | 3.5
Johnsie Devaughn | Introduction to Cloud Computing | 3.5
Quentin Brumsey | Concurrent Programming | 3.5
Farah Villafuerte | Pricing and Hedging | 3.5
Reyna Sergi | Advanced Computational Modeling in Biology and Biomaterials | 3.5
Kia Scheetz | Introduction to Cloud Computing | 3.5

## Original Data
Student Name | Course Name | Course Rating | Professor | Year Taken | Semester Taken | Course Rating | Professor Rating
Alex | Web Analytics | 2.5
Alex | Data Mining & Knowledge Discovery | 3.5
Alex | Statistical Learning | 3
Alex | Data Visualization | 3.5
Alex | Social Network Analysis | 2.5
Alex | Data Mining II | 3
Bob | Web Analytics | 3
Bob | Data Mining & Knowledge Discovery | 3.5
Bob | Statistical Learning | 1.5
Bob | Data Visualization | 5
Bob | Social Network Analysis | 3.5
Charlie | Web Analytics | 2.5
Charlie | Data Mining & Knowledge Discovery | 3
Charlie | Data Visualization | 3.5
Charlie | Data Mining II | 4
Doug | Data Mining & Knowledge Discovery | 3.5
Doug | Statistical Learning | 3
Doug | Data Mining II | 4.5
Doug | Data Visualization | 4
Doug | Social Network Analysis | 2.5
Emily | Web Analytics | 3
Emily | Data Mining & Knowledge Discovery | 4
Emily | Statistical Learning | 2
Emily | Data Visualization | 3
Emily | Data Mining II | 3
Emily | Social Network Analysis | 2
Frank | Web Analytics | 3
Frank | Data Mining & Knowledge Discovery | 4
Frank | Data Mining II | 3
Frank | Data Visualization | 5
Frank | Social Network Analysis | 3.5
Gary | Data Mining & Knowledge Discovery | 4.5
Gary | Social Network Analysis | 1
Gary | Data Visualization | 4

## Course Details
Course ID | Course Name | Professor 1 | Professor 2 | Professor 3 | School | Level | Type | Course Program | Course Progam Track
CS 526 | Enterprise and Cloud Computing | Hannelore Spece | Mel Kinnear | Linsey Rosen | Engineering and Science | Masters | Classroom | Computer Science | Cloud Computing
CS 550 | Computer Organization and Programming | Joanne Hessling | Kristle Junious | Clifford Mccubbin | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 570 | Introduction to Programming, Data Structures, and Algorithms | Basilia Pendergrast | Adah Souder | Tiffanie Rome | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 590 | Algorithms | Shalonda Winegarden | Juliann Millhouse | Slyvia Elson | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 510 | Principles of Programming Languages | Davina Vierling | Franchesca Almanzar | Renita Tyus | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 511 | Concurrent Programming | Salley Lex | Imelda Palm | Ross Slinkard | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 513 | Data Mining and Knowledge Management | Shauna Ornelas | Ofelia Maysonet | Romana Waddington | Engineering and Science | Masters | Classroom | Computer Science | Database
CS 520 | Introduction to Operating Systems | Blaine Chabot | Valentin Witkowski | Norma Mehr | Engineering and Science | Masters | Classroom | Computer Science | Operating Systems
CS 521 | TCP/IP Networking | Ashlea Currie | Tyler Fout | Jeanice Papadopoulos | Engineering and Science | Masters | Classroom | Computer Science | Mobile
CS 522 | Mobile Systems and Applications | Roosevelt Hendren | Johnie Shira | Melynda Darnell | Engineering and Science | Masters | Classroom | Computer Science | Cloud Computing
CS 524 | Introduction to Cloud Computing | Hermila Boe | Hedy Linz | Brigette Wenzl | Engineering and Science | Masters | Classroom | Computer Science | Cloud Computing
CS 526 | Enterprise and Cloud Computing | Shela Wolfrum | Ranee Beavers | Diedra Wester | Engineering and Science | Masters | Classroom | Computer Science | Cloud Computing
CS 537 | Interactive Computer Graphics | Kati Harvison | Lauran Okelley | Iris Disla | Engineering and Science | Masters | Classroom | Computer Science | Graphics
CS 541 | Artifical Intelligence | Iliana Nicoletti | Joanie Rotella | Alexandria Rivenburg | Engineering and Science | Masters | Classroom | Computer Science | Artificial Intelligence
CS 545 | Human Computer Interaction | Kathlyn Murphey | Deb Birkland | Suzy Rasheed | Engineering and Science | Masters | Classroom | Computer Science | Artificial Intelligence
CS 546 | Web Programming | Trent Petrillo | Erica Thoman | Milo Hitchman | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 548 | Enterprise Software Architecture and Design | Rikki Tarry | Yolande Pascoe | Nia Guadalupe | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 549 | Distributed and Cloud Computing | Esperanza Frahm | Krysten Devoe | Georgine Beaumont | Engineering and Science | Masters | Classroom | Computer Science | Cloud Computing
CS 561 | Database Management Systems I | Gisela Sleeper | Lucius Savidge | Jess Holmes | Engineering and Science | Masters | Classroom | Computer Science | Cyber Security
CS 573 | Fundamentals of Cybersecurity | Dalton Sugden | Kathlene Lamey | Corey Shue | Engineering and Science | Masters | Classroom | Computer Science | Cyber Security
CS 578 | Privacy in a Networked World | Verna Fee | Connie Thresher | Jesusita Dittman | Engineering and Science | Masters | Classroom | Computer Science | Networking
CS 600 | Advanced Algorithm Design and Implementation | Vallie Ruse | Rachael Divine | Joie Creech | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 677 | Parallel Programming for Many-core Processors | Marline Kamel | Demetra Krein | Essie Moorehead | Engineering and Science | Masters | Classroom | Computer Science | Programming
CS 694 | Advanced Computational Modeling in Biology and Biomaterials | Cherlyn Lamkin | Kimberly Ashbaugh | Faustino Lawhon | Engineering and Science | Masters | Classroom | Computer Science | Programming
FE 610 | Stochastic Calculus for Financial Engineers | Crissy Bazan | Chi Krogh | Emelia Minner | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 620 | Pricing and Hedging | Yong Costa | Lynwood Gillard | Jodi Croslin | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 630 | Portfolio Theory and Applications | Staci Mcdivitt | Stephen Tash | Rea Schlatter | Engineering and Science | Masters | Classroom | Financial Engineering | Software & Technology
FE 680 | Advanced Derivatives | Pearle Steffensen | Elinore Nye | Ivan Bodiford | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
FE 800 | Special Problems in Financial Engineering | Na Carruth | Linwood Tryon | Roslyn Matz | Engineering and Science | Masters | Classroom | Financial Engineering | Core
FE 900 | Thesis in Financial Engineering | Lorelei Madry | Lovella Bash | Hyacinth Tebo | Engineering and Science | Masters | Classroom | Financial Engineering | Core
FE 620 | Pricing and Hedging | Jaimee Mangan | Tim Thorington | Katrina Wyer | Engineering and Science | Masters | Classroom | Financial Engineering | Core
FE 621 | Computational Methods in Finance | Armando Branch | Rivka Bird | Phoebe Askey | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 630 | Portfolio Theory and Applications | Gala Copes | Shavon Vavra | Shay Ankrom | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 535 | Introduction to Financial Risk Management | Kerstin Sickler | Dawne Aube | Raguel Shugart | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 610 | Stochastic Calculus for Financial Engineers | Shaun Ardoin | Katherin Shellman | Maranda Scogin | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 635 | Financial Enterprise Risk Engineering | Burton Bad | Alyssa Touchstone | Kurt Shimek | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
FE 655 | Systemic Risk and Financial Regulation | Thurman Haakenson | Dyan Jared | Pearle Mcphatter | Engineering and Science | Masters | Classroom | Financial Engineering | Quantitative
SYS 605 | Systems Integration | Ulysses Mcleish | Sean Tremblay | Shaunta Bergman | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
EM 612 | Project Management of Complex Systems | Birgit Swager | Leena Spradley | Doris Felan | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
SYS 625 | Fundamentals of Systems Engineering | Edris Poff | Eric Maggi | Antonette Khouri | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
SYS 650 | System Architecture and Design | Maurice Fabry | Isa Serrata | Rhoda Kearl | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
EM 600 | Engineering Economics and Cost Analysis | Analisa Wendell | Enoch Cobos | Kaycee Whitford | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
EM 605 | Elements of Operations Research | Rachele Wilke | Ayanna Friel | Myrtle Newhard | Engineering and Science | Masters | Classroom | Financial Engineering | Systems & Management
MGT 615 | Financial Decision Making | Brandy Neth | Roger Christon | Marquetta Claude | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Business Intelligence
MIS 630 | Strategic Data Management | Randolph Lundell | Cheyenne Newcombe | Shon Montilla | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Business Intelligence
MIS 636 | Data Warehousing and Business Intelligence | Shanice Harley | Henry Metzger | Nicolette Desroches | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Business Intelligence
BIA 650 | Optimization and Process Analytics | Kaycee Valla | Buddy Maughan | Fredricka Fontanez | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 670 | Risk Management Methods & Applications | Katie Mattison | Andy Spell | Buford Bjerke | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 652 | Multivariate Data Analytics | Filomena Luckey | Nevada Georges | Alethia Yerian | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 654 | Experimental Design | Jina Haak | Elli Cornman | Rubie Noel | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
MIS 637 | Knowledge Discovery in Databases | Hye Hundt | Demetria Bradfield | Alexandria Hollon | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 656 | Statistical Learning & Analytics | Ray Outlaw | Carita Becenti | Ellena Bulluck | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 658 | Social Network Analytics | Jolynn Burkhard | Shaunte Bischof | Benny Mckane | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 660 | Web Analytics | Crissy Weidman | Consuelo Poche | Margert Ferguson | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 672 | Marketing Analytics | Virgen Quillin | Scotty Burchill | Bruna Gibbs | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIS 674 | Supply Chain Analytics | Yolande Champine | Janice Delph | Yoshiko Derrickson | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 676 | Data Stream Analytics | Wynell Detrick | Florrie Devers | Adrien Duggins | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Analytics
BIA 678 | Big Data Seminar | Reggie Elser | Dori Braaten | Chara Phaneuf | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Business Intelligence
BIA 686 | Applied Analytics in a World of Big Data | Lacey Payer | Shella Berger | Gaye Busbee | Engineering and Science | Masters | Classroom | Business Intelligence & Analytics | Business Intelligence

## Student Details
Student ID | Student Name | Student Program
10001 | Karolina Nowak | Financial Engineering
10002 | Ajai Thomas | Computer Science
10003 | Keyur Doshi | Computer Science
10004 | Danica Tarin | Business Intelligence & Analytics
10005 | Anuj Batra | Computer Science
10006 | Brian Beesley | Financial Engineering
10007 | Yun Chen | Financial Engineering
10008 | Tao Feng | Computer Science
10009 | Herschel Doughty | Computer Science
10010 | Jigar Jain | Business Intelligence & Analytics
10011 | Jia Liu | Business Intelligence & Analytics
10012 | Jian Tang | Business Intelligence & Analytics
10013 | Linette Lamagna | Business Intelligence & Analytics
10014 | Kenyetta Troutman | Business Intelligence & Analytics
10015 | So Overturf | Business Intelligence & Analytics
10016 | Damion Brady | Business Intelligence & Analytics
10017 | Quincy Prisco | Business Intelligence & Analytics
10018 | Sue Wilkin | Business Intelligence & Analytics
10019 | Suellen Wald | Business Intelligence & Analytics
10020 | Adria Clickner | Business Intelligence & Analytics
10021 | Asley Taff | Business Intelligence & Analytics
10022 | Patricia Remley | Business Intelligence & Analytics
10023 | Malinda Troncoso | Business Intelligence & Analytics
10024 | Jenna Sandell | Business Intelligence & Analytics
10025 | Page Mell | Business Intelligence & Analytics
10026 | Farah Villafuerte | Business Intelligence & Analytics
10027 | Anjelica Biscoe | Business Intelligence & Analytics
10028 | Romona Mishoe | Business Intelligence & Analytics
10029 | Bonny Pett | Computer Science
10030 | Vincenzo Longshore | Computer Science
10031 | Kyra Stecklein | Computer Science
10032 | Deb Pietsch | Computer Science
10033 | Alvaro Legrande | Computer Science
10034 | Jc Milburn | Computer Science
10035 | Hisako Crumbley | Computer Science
10036 | Yu Strobl | Computer Science
10037 | Samella Scheffel | Computer Science
10038 | Darius Brouwer | Computer Science
10039 | Keesha Montalbo | Computer Science
10040 | Classie Elswick | Computer Science
10041 | Derrick Chittenden | Computer Science
10042 | Jetta Hinkley | Computer Science
10043 | Kia Scheetz | Computer Science
10044 | Shenika Parson | Computer Science
10045 | Mui Choy | Computer Science
10046 | Teressa Thornhill | Computer Science
10047 | Dwana Rybicki | Computer Science
10048 | Reyna Sergi | Computer Science
10049 | Fonda Parkes | Computer Science
10050 | Despina Sires | Computer Science
10051 | Thi Sylvester | Computer Science
10052 | Marcella Ostrander | Computer Science
10053 | Jeromy Maisch | Computer Science
10054 | Velma Effinger | Computer Science
10055 | Malka Gushiken | Computer Science
10056 | Ka Unsworth | Computer Science
10057 | Bruna Lachermeier | Computer Science
10058 | Gabriela Kiesling | Computer Science
10059 | Phylicia Raulerson | Computer Science
10060 | Terina Strauss | Computer Science
10061 | Altagracia Guerrette | Computer Science
10062 | Shonda Mccarter | Computer Science
10063 | Pei Nagel | Computer Science
10064 | Teri Chasse | Computer Science
10065 | Kendra Salinas | Computer Science
10066 | Lauri Lundeen | Computer Science
10067 | Ramiro Sells | Computer Science
10068 | Melva Basil | Computer Science
10069 | Blaine Candela | Computer Science
10070 | Junior Dowdle | Computer Science
10071 | Tyson Frix | Computer Science
10072 | Rosella Newcomer | Computer Science
10073 | Randell Werner | Computer Science
10074 | Effie Endicott | Computer Science
10075 | Noelle Moll | Computer Science
10076 | Sana Manion | Computer Science
10077 | Brandee Ferrier | Computer Science
10078 | Porsha Rolfes | Computer Science
10079 | Quentin Brumsey | Computer Science
10080 | Elenor Angell | Computer Science
10081 | Ettie Lubinsky | Computer Science
10082 | Liliana Gaitan | Computer Science
10083 | Samara Taubman | Computer Science
10084 | Sterling Krejci | Computer Science
10085 | Jerome Sharman | Computer Science
10086 | Stephany Mcgranahan | Financial Engineering
10087 | Julianne Korb | Financial Engineering
10088 | Tamica Fauntleroy | Financial Engineering
10089 | Mabel Lohr | Financial Engineering
10090 | Cole Mcnichols | Financial Engineering
10091 | Johnsie Devaughn | Financial Engineering
10092 | Cristine Deming | Financial Engineering
10093 | Addie Gin | Financial Engineering
10094 | Tobi Dantin | Financial Engineering
10095 | Li Condrey | Financial Engineering
10096 | Torie Mcsherry | Financial Engineering
10097 | Shizuko Melton | Financial Engineering
10098 | Jack Robin | Financial Engineering
10099 | Janita Banaszak | Financial Engineering
10100 | Krystyna Yaple | Financial Engineering